10K committee catch-up-20260811_180012-Meeting Transcript

11 August 2026, 06:00pm

21m 08s

Deepa Sharma started transcription

Deepa Sharma   0:05

Okay, shall we start? We've got both Jos today, which always confuses the minutes, ha, Jo Bennett and Jo Marsh, and me and Alan. Right.

Jo Bennett   0:15

Ha, story of our lives. I'll be Jo B if it helps.

Jo Marsh   0:18

And I'm Jo M. Or the taller Jo.

Alan Pryce   0:21

Ha. Right, the ten K. Six weeks out. Where are we.

Deepa Sharma   0:26

So the date's locked, the twenty-eighth of September, and we said fifteen pounds entry, that hasn't changed?

Alan Pryce   0:33

Fifteen, yeah, that's confirmed.

Jo Marsh   0:35

The big worry for me is marshals. We had barely enough last year and someone nearly went the wrong way at the river turn.

Deepa Sharma   0:43

Yes, that was chaos. How many do we need?

Jo Marsh   0:46

For that route, properly, fourteen. We had nine last year.

Alan Pryce   0:51

So who's chasing marshals? That's the priority.

Jo Marsh   0:54

I'll take that. I'll sort the marshals, I've got the list from last year and I'll ring round and get us up to fourteen.

Deepa Sharma   1:01

Brilliant, thank you, Jo. So Jo Marsh is doing marshals.

Jo Marsh   1:05

Jo M, marshals, yes.

Jo Bennett   1:08

And what about first aid? Because she, sorry, because Jo, the other one, mentioned last time we can't just rely on one St John's person for a whole ten K.

Jo Marsh   1:17

Yeah that was me, we were dangerously light on cover.

Alan Pryce   1:20

So do we need to book proper cover?

Jo Bennett   1:23

We do. I'll do that, I'll sort the first aid cover. I'll get a quote from St John Ambulance for two crews for the day, and confirm it once you're all happy with the cost.

Deepa Sharma   1:32

Good. So Jo Bennett's on first aid, Jo Marsh is on marshals, everyone clear which Jo's doing what?

Alan Pryce   1:38

Ha, just about.

Jo Bennett   1:40

Marshals is her, first aid is me. Got it.

Deepa Sharma   1:43

Now the route. Alan, that's you, isn't it, you were dealing with the council?

Alan Pryce   1:48

Yeah. So the route's basically last year's, but they've resurfaced part of the towpath and I need to check it's open. And there's the road-closure order for the first half mile on the main road.

Deepa Sharma   1:58

Is the closure sorted?

Alan Pryce   2:00

Not yet. He said, the chap at the council, he said the application takes four weeks to process, so we're cutting it fine actually.

Jo Marsh   2:07

Four weeks and we're six weeks out, that's alright, just.

Alan Pryce   2:11

Just. So I'll get the road-closure application in this week, no later, and confirm the towpath's reopened. If that closure doesn't come through we've got no start line.

Deepa Sharma   2:20

That's a real risk, the permit. Flag it. If it's not confirmed by, say, two weeks out, we need a plan B route.

Alan Pryce   2:27

Agreed. I'll chase it hard.

Jo Bennett   2:30

Can I ask about the shirts? People kept asking last year if there's a finisher's shirt or a medal.

Deepa Sharma   2:36

We did medals last year, not shirts. Medals are cheaper and people love them.

Jo Marsh   2:41

Medals, definitely. Shirts, you get the sizes wrong and you're left with two hundred extra larges.

Deepa Sharma   2:47

Ha, true. So we're agreed, medals again, not shirts. Who ordered them last year?

Jo Bennett   2:52

That was, oh, was that you Deepa?

Deepa Sharma   2:54

It was me, yeah. I'll reorder the medals, same as last year, we need, if we're expecting three hundred runners, I'll order three hundred and fifty to be safe.

Alan Pryce   3:03

Three fifty, good.

Deepa Sharma   3:05

So that's me on the medals. And the social media, we've been rubbish at it this year, we've barely posted.

Jo Marsh   3:11

We really have. Entries are down on this point last year because of it, I reckon.

Deepa Sharma   3:16

I think that's exactly why. I'll take the social media. I'll do a proper push, a post every couple of days from now till race day, and get the entry link out everywhere.

Jo Bennett   3:25

Good, because we want the numbers up. He was saying, the treasurer, that we need about two-eighty entries to break even after costs.

Deepa Sharma   3:33

Two-eighty to break even, yeah. So the social push matters. Right, I think we've covered it. Let me just check I've got everyone's jobs right, because of the two Jos.

Alan Pryce   3:42

Go on, read it back.

Deepa Sharma   3:44

So. Jo Marsh, marshals, getting us to fourteen. Jo Bennett, first aid, quote from St John's for two crews. Alan, road-closure application in this week and check the towpath. Me, reorder three hundred and fifty medals and run the social media.

Jo Marsh   3:59

Perfect, that's me right.

Jo Bennett   4:01

And me, yep, first aid.

Alan Pryce   4:03

Correct.

Deepa Sharma   4:05

Lovely. And the big risk we're all watching is the road-closure permit, because no permit, no start. Alan's on it.

Alan Pryce   4:12

I'm on it.

Deepa Sharma   4:14

Great. Same time in a fortnight? We'll need to be further along by then.

Jo Bennett   4:19

Fortnight works.

Jo Marsh   4:20

Yep.

Alan Pryce   4:21

See you all then. Thanks.

Deepa Sharma   4:23

Thanks everyone, bye.

Deepa Sharma stopped transcription