Client T802 Meridian Ortho Tech File review weekly-20260701_090012-Meeting Transcript

1 July 2026, 09:00am

17m 51s

Jacqui Fox started transcription

Jacqui Fox   0:03
Morning all. I'll give it thirty seconds for Dermot and then we'll just crack on, because I know Ffion has to drop at half past.

Ffion Hargreaves   0:12
Twenty five past actually, sorry.

Jacqui Fox   0:15
Twenty five past. Right, no, that's fine, we'll be done well before that. Okay so I went through the tracker last night, so just to give you the headline before we step through. We were at forty one documents sitting in the not started column last week, we're at thirty three this morning, so that's eight moved which is the best week we've had.
Most of that is the labelling pack, so it's not as dramatic as it sounds, those are short documents. But it's movement.

Ffion Hargreaves   0:44
That's Priya's work mostly, she's been going at it.

Jacqui Fox   0:48
Yeah, and it shows. Okay so if I step down through the core areas the same as always. Risk first. So David, you've had the risk management plan sitting with you since, I think it went over on the Thursday?

David Didsbury   1:02
It did, yeah. I've read it. I haven't written it up yet.

Jacqui Fox   1:06
Okay.

David Didsbury   1:08
It's broadly fine. There's two things. The severity scale, they've got five bands, and the top two bands are described almost identically. So catastrophic and critical, if you read the wording, you couldn't reliably put a hazard in one rather than the other. That needs fixing before anybody populates the matrix, otherwise you're going to have to redo it.
And then the second thing is there's no rationale anywhere for the probability bands. It's the standard set out of 14971, one in a hundred, one in a thousand and so on, but there's nothing saying what an event is.

Rebecca Gill   1:44
Is that per use or per device or per patient, you mean.

David Didsbury   1:47
Per what, exactly. Because if it's per device over a five year life that's a completely different number to per procedure.

Dermot Nally   1:56
Sorry, I'm in, I was in the wrong meeting.

Jacqui Fox   1:59
No bother Dermot, we're on risk, we'll come to you in a minute. David, so on those two points, is that something you can write up as comments in the document?

David Didsbury   2:09
I can. It'll be Friday though, I'm on site Wednesday and Thursday.

Jacqui Fox   2:13
Friday's fine. Rebecca, does that block you on the matrix?

Rebecca Gill   2:18
It blocks the population of it, yeah, because I'd just be putting numbers in that we then move. I can do the structure of it, so the columns, the sheets, the pre and post control columns, that's not affected. So I'll build the shell this week and then fill it once David's comments are in.

Jacqui Fox   2:36
Perfect, that's the right way round. So risk stays amber then, but for a good reason. Okay, software. Dermot.

Dermot Nally   2:45
Yeah. So the navigation app. We've done the split, so the app is now formally two items, there's the planning module and there's the intraoperative display.

David Didsbury   2:56
Right.

Dermot Nally   2:58
Which we should have done a year ago, but there we are. The reason for doing it is the classification. The planning module we're saying is class B, and the display, because it's showing position during the procedure, that's C.

David Didsbury   3:14
Who's signed that off?

Dermot Nally   3:16
Nobody yet, that's my proposal.

David Didsbury   3:19
Okay, because that's the bit that'll get looked at hardest. Splitting is fine, splitting is normal, but you need the justification written down for why the planning module can't contribute to a hazardous situation. And I'd want to see that before it goes anywhere near the notified body.

Dermot Nally   3:36
Understood. I'll draft that.

Jacqui Fox   3:39
And when do you think, Dermot?

Dermot Nally   3:42
Two weeks. It's not a long document but I want Marcus to look over it.

Jacqui Fox   3:47
Okay so that's the fifteenth. I'll put it in as the fifteenth. Sanjay, you had the UDI piece.

Sanjay Iyer   3:55
I did, yeah. So of the twenty two references, eighteen are in EUDAMED correctly. Four are not, and three of those four are the ones where we changed the packaging configuration in, I want to say March.

Jacqui Fox   4:10
March, yeah.

Sanjay Iyer   4:12
So those need new DIs, which is fine, that's just work. The fourth one I don't understand yet. It's in there twice with two different basic UDI DIs and I can't tell you how that happened.

Ffion Hargreaves   4:26
Is that the eight millimetre?

Sanjay Iyer   4:28
It's the eight, yeah.

Ffion Hargreaves   4:30
That one was submitted by the distributor originally, before we brought it back in house. So that might be it.

Sanjay Iyer   4:37
Ah. Right, that would explain it. Okay, I'll go back through the distributor correspondence then.

Jacqui Fox   4:44
Good. And Sanjay, timeline on that?

Sanjay Iyer   4:47
The three new DIs, this week. The duplicate, I genuinely don't know until I've looked, it could be a phone call or it could be a month.

Jacqui Fox   4:56
That's fair. I'll note the three as this week and leave the other one open with a note. Okay, clinical evaluation.

Ffion Hargreaves   5:04
That's me and it's not good news. Our clinical evaluator has gone off, she's not coming back before September.

Jacqui Fox   5:12
Ohh.

Ffion Hargreaves   5:14
Yeah. So the CER update is stalled. There's a draft, it's about sixty percent, and nobody internally can finish it.

Rebecca Gill   5:23
Is it the literature search that's outstanding or the appraisal?

Ffion Hargreaves   5:27
The search is done, and it's documented, so that bit's fine. It's the appraisal and then the conclusions.

Rebecca Gill   5:35
That's the harder half unfortunately.

Ffion Hargreaves   5:38
It is. So I think we need somebody.

Jacqui Fox   5:41
We have people. I'd want to put Louise on that rather than one of ours generally, because she's done the orthopaedic ones. Let me check her availability today and come back to you with a name and a rate by tomorrow.

Ffion Hargreaves   5:55
That'd be great, thank you.

Jacqui Fox   5:58
Okay. Supplier agreements, this is the one that's been sitting.

Ffion Hargreaves   6:03
I know.

Jacqui Fox   6:04
I'm not having a go.

Ffion Hargreaves   6:06
No, you can have a go, it's three weeks now. It's with legal. I've chased twice.

Jacqui Fox   6:12
Is it all of them or some of them?

Ffion Hargreaves   6:14
It's the two coating suppliers. The rest are done and I could send those today.

Jacqui Fox   6:20
Send the ones you have. Genuinely, don't wait for the set. If we get the seven we can start reviewing seven.

Ffion Hargreaves   6:27
Okay, yeah, that's sensible. I'll send those over this afternoon.

Jacqui Fox   6:31
And who's reviewing those our side, is that you Rebecca?

Rebecca Gill   6:35
I can. It depends on the matrix timing, but yes, I'd rather have them than not.

Jacqui Fox   6:41
Okay. She'll pick that up then and let us know if it's too much.

Dermot Nally   6:47
Sorry, can I go back to the classification thing for one second.

Jacqui Fox   6:50
Course.

Dermot Nally   6:52
David, when you say justification written down, do you mean in the software development plan or somewhere separate?

David Didsbury   6:59
In the plan. Don't create a new document for it. It goes in the section where you describe the software system, you state the items, you state the class of each, and then a paragraph each on why. Two or three paragraphs total, it's not an essay.

Dermot Nally   7:14
Right, that's much less work than I thought it was.

David Didsbury   7:17
It usually is. The thinking is the work, the writing's twenty minutes.

Jacqui Fox   7:22
Okay. Anything else on software before I move on? No. Right, labelling and IFU.

Sanjay Iyer   7:29
That's largely Fiona's, sorry, Ffion, I say it wrong every week.

Ffion Hargreaves   7:34
Everyone does, don't worry about it.

Sanjay Iyer   7:37
The symbols review is finished. There were two symbols on the outer carton that aren't in 15223 anymore, so those are coming off. The IFU itself is with the translators.

Jacqui Fox   7:50
How many languages?

Sanjay Iyer   7:52
Twenty four.

Jacqui Fox   7:53
And when do they come back?

Sanjay Iyer   7:56
They said four weeks from the twentieth. So the eighteenth of July, thereabouts.

Jacqui Fox   8:02
Okay. And is there a checking step after that?

Ffion Hargreaves   8:06
There is, and that's a problem actually, because we normally get the local distributors to check and two of them have said they haven't the resource this year.

Jacqui Fox   8:15
Which two?

Ffion Hargreaves   8:17
Poland and Portugal.

Jacqui Fox   8:19
Okay. Park that, but flag it, because that will bite in August if we don't sort it now. Can you find out what they'd need to do it, whether it's a money thing or a people thing.

Ffion Hargreaves   8:31
Yeah, I'll ask.

Jacqui Fox   8:33
Right. Anything anyone wants to raise that I haven't covered.

Rebecca Gill   8:38
Just one, and it's minor. The tracker column for owner, half of them say Meridian and half of them say a person. Can we make them all say a person, because otherwise I don't know who to chase.

Ffion Hargreaves   8:51
That's fair. I'll go through and put names on.

Jacqui Fox   8:54
Good shout Rebecca. Right, that's us. I'll send the minutes out this afternoon and I'll flag the CER thing separately by email, Ffion, because that's the one that worries me most.

Ffion Hargreaves   9:05
Agreed. Thanks Jacqui.

David Didsbury   9:08
Cheers.

Dermot Nally   9:09
Bye now.

Sanjay Iyer   9:10
Thanks all.

Jacqui Fox stopped transcription