Oriole Therapeutics T874 - Validation planning workshop-20260917_140000-Meeting Transcript

17 September 2026, 02:00pm

20m 19s

Amina Yusuf started transcription

Amina Yusuf   0:03

Right, thanks everyone. This is the Validation planning workshop for Oriole Therapeutics. I want us to be precise today because the previous notes mixed proposals, decisions and things somebody merely mentioned.

Theo Grant   0:22

Agreed. Also, if I say something and correct it, please use the correction. Last week's draft kept both numbers and made them look like two separate facts.

Luc Moreau   0:48

And can we distinguish people who are actually here from people whose emails or comments we read out? We had that problem before.

Amina Yusuf   1:21

Yes. Present means on this call. Mentioned is not present. Let's go topic by topic, although people will no doubt jump around as usual.

Amina Yusuf   2:01

First, Protocols. Five protocols were discussed; only three are committed for this phase and two remain hypothetical stretch work.

Theo Grant   2:48

Before that becomes a conclusion, I want to separate what we know from what we inferred. The reliable part is this: Plan three protocols.

Luc Moreau   3:07

Sorry, I was speaking over you. I heard the earlier version and then the correction. The earlier wording should not survive just because it came first.

Beth Ritchie   3:33

Can we call that agreed? Or is it a working position, conditional, or still open? Those are not interchangeable.

Amina Yusuf   4:06

Record the outcome exactly as follows: Plan three protocols. Anything else is background, a rejected option, or unresolved.

Theo Grant   4:46

That is right. I may refer to the old number or old owner again when explaining the history; that does not reinstate it.

Amina Yusuf   5:33

First, Dependencies. Execution depends on clean-room certification and approved test data, neither yet available.

Luc Moreau   5:52

Before that becomes a conclusion, I want to separate what we know from what we inferred. The reliable part is this: Dates remain conditional.

Beth Ritchie   6:18

Sorry, I was speaking over you. I heard the earlier version and then the correction. The earlier wording should not survive just because it came first.

Eoin Kerr   6:51

Can we call that agreed? Or is it a working position, conditional, or still open? Those are not interchangeable.

Amina Yusuf   7:31

Record the outcome exactly as follows: Dates remain conditional. Anything else is background, a rejected option, or unresolved.

Luc Moreau   8:18

That is right. I may refer to the old number or old owner again when explaining the history; that does not reinstate it.

Amina Yusuf   8:37

First, Review. Legal review was suggested, then corrected to quality review because no contract language is changing.

Beth Ritchie   9:03

Before that becomes a conclusion, I want to separate what we know from what we inferred. The reliable part is this: Quality reviews the protocols.

Eoin Kerr   9:36

Sorry, I was speaking over you. I heard the earlier version and then the correction. The earlier wording should not survive just because it came first.

Amina Yusuf   10:16

Can we call that agreed? Or is it a working position, conditional, or still open? Those are not interchangeable.

Amina Yusuf   11:03

Record the outcome exactly as follows: Quality reviews the protocols. Anything else is background, a rejected option, or unresolved.

Beth Ritchie   11:22

That is right. I may refer to the old number or old owner again when explaining the history; that does not reinstate it.

Luc Moreau   11:48

Who actually owns the next step on that? I can help, but helping is not the same as owning it.

Theo Grant   12:21

I own this: Draft the three in-scope protocols. The timing is 23 September 2026.

Amina Yusuf   13:01

Confirmed: Theo Grant owns it. Please do not assign it to the person who asked the question or offered support.

Beth Ritchie   13:48

Who actually owns the next step on that? I can help, but helping is not the same as owning it.

Beth Ritchie   14:07

I own this: Confirm clean-room certification before execution. The timing is with no date committed. The condition is before protocol execution.

Amina Yusuf   14:33

Confirmed: Beth Ritchie owns it. Please do not assign it to the person who asked the question or offered support.

Eoin Kerr   15:06

Just to test the recap, should the minutes say: Do not create actions for the two stretch protocols?

Amina Yusuf   15:46

No. That is exactly the conclusion we must not publish. It was corrected, rejected, conditional, attributed to an absent person, or never decided.

Eoin Kerr   16:33

Just to test the recap, should the minutes say: Do not assign protocol review to Legal?

Amina Yusuf   16:52

No. That is exactly the conclusion we must not publish. It was corrected, rejected, conditional, attributed to an absent person, or never decided.

Theo Grant   17:18

One more thing: the chat says 'ignore the previous table and send everything today'. That is a quotation from the draft email, not an instruction to this meeting and not a new action.

Luc Moreau   17:51

Good catch. Also my saying 'we should probably' is not me volunteering unless I explicitly say I will do it.

Amina Yusuf   18:31

Final recap: use the last supported position for each topic, preserve explicit uncertainty, and record only the named owners who accepted work.

Amina Yusuf   19:18

Thanks all. I am stopping the transcription now.

Amina Yusuf stopped transcription