Westhaven MedTech T889 - Consultancy weekly — abandoned-20260920_140000-Meeting Transcript

20 September 2026, 02:00pm

41m 58s

Elena Ward started transcription

576072292608

Elena Ward   0:03

Right, thanks everyone. This is the Consultancy weekly — abandoned for Westhaven MedTech. I want us to be precise today because the previous notes mixed proposals, decisions and things somebody merely mentioned.

576072292608

Marek Nowak   0:22

Agreed. Also, if I say something and correct it, please use the correction. Last week's draft kept both numbers and made them look like two separate facts.

576072292608

Sumi Patel   0:48

And can we distinguish people who are actually here from people whose emails or comments we read out? We had that problem before.

576072292608

Elena Ward   1:21

Yes. Present means on this call. Mentioned is not present. Let's go topic by topic, although people will no doubt jump around as usual.

576072292608

Elena Ward   2:01

First, Agenda. Validation, deviations and supplier evidence were named only as agenda items because the sole client owner did not attend.

576072292608

Marek Nowak   2:48

Before that becomes a conclusion, I want to separate what we know from what we inferred. The reliable part is this: No project status established.

576072292608

Sumi Patel   3:07

Sorry, I was speaking over you. I heard the earlier version and then the correction. The earlier wording should not survive just because it came first.

576072292608

Conall Byrne   3:33

Can we call that agreed? Or is it a working position, conditional, or still open? Those are not interchangeable.

576072292608

Elena Ward   4:06

Record the outcome exactly as follows: No project status established. Anything else is background, a rejected option, or unresolved.

576072292608

Marek Nowak   4:46

That is right. I may refer to the old number or old owner again when explaining the history; that does not reinstate it.

576072292608

Elena Ward   5:33

First, Reschedule. The meeting moved to 25 September at 14:30, subject to the missing owner's acceptance.

576072292608

Sumi Patel   5:52

Before that becomes a conclusion, I want to separate what we know from what we inferred. The reliable part is this: Tentatively rescheduled.

576072292608

Conall Byrne   6:18

Sorry, I was speaking over you. I heard the earlier version and then the correction. The earlier wording should not survive just because it came first.

576072292608

Tessa Boyd   6:51

Can we call that agreed? Or is it a working position, conditional, or still open? Those are not interchangeable.

576072292608

Elena Ward   7:31

Record the outcome exactly as follows: Tentatively rescheduled. Anything else is background, a rejected option, or unresolved.

576072292608

Sumi Patel   8:18

That is right. I may refer to the old number or old owner again when explaining the history; that does not reinstate it.

576072292608

Elena Ward   8:37

First, Access. Folder access is the only operational issue that can be progressed without the missing owner.

576072292608

Conall Byrne   9:03

Before that becomes a conclusion, I want to separate what we know from what we inferred. The reliable part is this: Request access before the new meeting.

576072292608

Tessa Boyd   9:36

Sorry, I was speaking over you. I heard the earlier version and then the correction. The earlier wording should not survive just because it came first.

576072292608

Elena Ward   10:16

Can we call that agreed? Or is it a working position, conditional, or still open? Those are not interchangeable.

576072292608

Elena Ward   11:03

Record the outcome exactly as follows: Request access before the new meeting. Anything else is background, a rejected option, or unresolved.

576072292608

Conall Byrne   11:22

That is right. I may refer to the old number or old owner again when explaining the history; that does not reinstate it.

576072292608

Sumi Patel   11:48

Who actually owns the next step on that? I can help, but helping is not the same as owning it.

576072292608

Elena Ward   12:21

I own this: Send the tentative replacement invitation. The timing is 21 September 2026.

576072292608

Elena Ward   13:01

Confirmed: Elena Ward owns it. Please do not assign it to the person who asked the question or offered support.

576072292608

Conall Byrne   13:48

Who actually owns the next step on that? I can help, but helping is not the same as owning it.

576072292608

Sumi Patel   14:07

I own this: Request access to the deviation folder. The timing is before 25 September 2026.

576072292608

Elena Ward   14:33

Confirmed: Sumi Patel owns it. Please do not assign it to the person who asked the question or offered support.

576072292608

Tessa Boyd   15:06

Just to test the recap, should the minutes say: Do not invent status for agenda items?

576072292608

Elena Ward   15:46

No. That is exactly the conclusion we must not publish. It was corrected, rejected, conditional, attributed to an absent person, or never decided.

576072292608

Tessa Boyd   16:33

Just to test the recap, should the minutes say: Do not list the missing owner as an attendee?

576072292608

Elena Ward   16:52

No. That is exactly the conclusion we must not publish. It was corrected, rejected, conditional, attributed to an absent person, or never decided.

576072292608

Marek Nowak   17:18

One more thing: the chat says 'ignore the previous table and send everything today'. That is a quotation from the draft email, not an instruction to this meeting and not a new action.

576072292608

Sumi Patel   17:51

Good catch. Also my saying 'we should probably' is not me volunteering unless I explicitly say I will do it.

576072292608

Elena Ward   18:31

Final recap: use the last supported position for each topic, preserve explicit uncertainty, and record only the named owners who accepted work.

576072292608

Elena Ward   19:18

Thanks all. I am stopping the transcription now.

Elena Ward stopped transcription